2024

Project Management

CAR GALLERY

**Group Members:**

Amjad Abdalmana

Faisal Basaleem

Hatem AL-Douh

Mohammed Baqshmer

Mutasem Al-Ahmadi

Professor's Supervision: Shahnaz Bawazeer

**Abstract:**In this project well talk about Car Gallery and how to manage it

**Introduction:**We Student team that create Project for Selling Cars in Gallery store,

And We found a place to do that So we import Cars from Company And sell it with a big team that assist us

**Problem statement:**

**Project scope:**The scope of the project includes the following key areas:

|  |  |
| --- | --- |
| 1- | Location determination |
| 2- | Exhibition décor |
| 3- | Merchandise |
| 4- | Labor force |
| 5- | Preparing for the Opening |
| 6- | The Opening of the Car Gallery |

**Project plan:**

1. **Project Overview:**

The project's goal is to create a system that can be used to manage and open a car gallery store

1. **Project Goal:**

Open a car gallery store

1. **Key Features:**

• **Project Timeline:**The project will commence on [2024/2/1] and is expected to be completed within [2024/5/30]. The timeline will be closely monitored and any deviations or delays will be addressed promptly to ensure timely completion

* Phase 1: Location determination - 13 days 2024(2/1 – 2/13).
* Phase 2: Exhibition décor - 15 days 2024(2/14 – 2/21).
* Phase 3: Merchandise- 49 days 2024(3/3 – 4/17).
* Phase 4: Labor force – 9.5 days 2024(4/8 – 4/21).
* Phase 5: Preparing for the Opening – 41 days 2024(4/21 – 5/30).
* Phase 6: Opening – 1 days 2024(5/30 – 5/31).  
  • **Project Team:**The project team consists of the following key roles:  
  1- Project Manager: Responsible for overall project coordination and  
  management.  
  2- Rent: The cost of the location.  
  3- Client: contract a deal with them.

4- Receipt: an employee that get cars from the Port.  
5- staff: an employee that works at the shop.

6- HR: who make interview with the new employees

7- Designer: make sure the Exhibition décor is perfect

• **Work Breakdown Structure (WBS):**

A comprehensive WBS will be developed to outline the tasks and sub-tasks required for the successful completion of the project.

|  |
| --- |
|  |

• **Calendar and Resources:**A detailed calendar will be created to schedule project activities and allocate resources effectively.

**-Calendar:**

|  |
| --- |
|  |
|  |

**-Recources:**

|  |
| --- |
|  |